## waterfall
EB1 | time axis 2026-08-31 to 2026-11-27
PCBA | Task | Validation | Start | End | Remark
Baseboard
| Early Bring up in factory |  | 2026-09-06 | 2026-09-06 | Wistron- EE/DC/BMC/EA(Standby) NVIDIA- Kelvin/CK | bar: 2026-09-06
Phase1 w/o Module Bring up in LAB
| Bring up in SC |  | 2026-09-10 | 2026-09-10 | bar: 2026-09-10
EB1 full qual
BayC board
| Early Bring up in factory |  | 2026-09-06 | 2026-09-06 | bar: 2026-09-06
Bring up in LAB
EB1 full qual
Tester
Early w/o module Bring up in factory
Bring up in LAB
Bring up in SC
w/ module Bring up in SC
CPU module
| Early LB bring up in factory |  | 2026-09-20
| Bring up in LAB |  | 2026-09-23
Bring up in SC
Early Chip bring up in factory
Bring up in LAB
Bring up in SC
EB1 full qual
L10
Phase1 w/o Module Bring up in SC
Phase2 w/ Module Bring up in SC
TS1 | time axis 2026-08-31 to 2026-11-27
Function | Task | Validation | Start | End | Remark
L10
Mechenical
Thermal
Reliability
| Structure test |  |  |  | 4.5周測試
| Reliability |  |  |  | 7周測試
| Packing |  |  |  | 2周測試+2周report
EMC
Validation
Cert
Safety
Validation
Cert
EB2 | time axis 2026-08-31 to 2026-11-27
Function | Task | Validation | Start | End | Remark
Baseboard
BayC board
CPU module
L10
TS2 | time axis 2026-08-31 to 2026-11-27
Function | Task | Validation | Start | End | Remark
L10
Mechenical
Thermal
Reliability
Structure test
Reliability
EMC
Validation
Cert
Safety
Validation
Cert